## Impacts
Title | Details | Difficulty | Status | Notes
Remove Data Watcher | When I first learned Blazor, I needed this. I don't think is needed now. | Medium - Took out the DataGateway code | Done Except Docs & Testing | Make sure to update the User's Guide
Remove Binding | Take out code for AllowBinding and Code Generation of ItemCallback | Medium - Effects code generation and GUI | Done Except Docs & Testing | Required update to DataJuggler.Net (.NET Framework version)
Replace Stored Procedure Manager | Stored Procs were too object oriented. Replace with XML loaded. | Major - Remove code generated stored procs and builders. | Planning | Template Change Also
Remove App Logic Component | Move Connection to DAC | Medium - Move everything to DAC - Investigate removing Data Operations | Planning | Template Change Also
Move Gateway to DAC | This gets it down to 2 projects | Medium - Code Generation and Custom Methods has to change | Planning | Template Change Also
Move Object Library To DAC | This gets it down 1 project | Medium | Planning | Template Change Also
Visual Studio Project Updater | Redesign form and control for 1 project | Medium | Planning
Update Documentation | Lots of the Users Guide and Quick Start Will Change | Medium | Planning
Benchmarks | Test if there are any performance gaines | Easy | Planning
Update Project Template | This goes from a multi-project template to single | Medium | Planning | Build Copy should handle this
Change Custom Method Editors | Use XML and make sure build rewrites base and custom methods | Major | Planning
New Install Release | Update the installer | Easy | Planning
Fix Indent for Custom Methods | Indent is 1 tab to indented. | Easy | Done Except Testing | VS 2022 indent doesn't like indented regions
Remove Order By Descending | Field Set